## Sheet1
Task | Progress | Who | Requirement | Time Estimate | Start Date | Goal Met
Music | Done | Alex, Outside Source |  |  | 2011-03-03
Music - Actual Music | Done | Out Side Source |  | 1day |  | yes
Music - Coded player | Done | Alex | 3 | 1day |  | yes
Art | Never Ending | All & Outside Sources |  |  | 2011-03-03
Art - Characters | As needed | Alex | Char To Make | 1day each |  | so far
Art - Tiles | As needed | Alex, Matt | Tile To Make | 1day each |  | so far
Art - Skills | As Needed | John | Skill To Make | 1day each |  | so far
Art - Misc(Menus/ Buttons) | Not Started | Alex | As Needed | 1day each |  | so far
Text Printer | Done | Alex |  | 1day | 2011-03-03 | yes
Engins Graphics, Sound, Networking | Done | All |  | 1.5 weeks | 2011-03-03 | Late 2 weeks
User Input | Done | Matt |  | 2days | 2011-03-03 | yes
Entities | Done | Alex*, John, Matt |  | 4days | 2011-03-03 | Yes
Entity - Player | Done | Matt | 13,6
Entity - Minion | Done | Alex | 13,6
Entity - Boss | Done | Alex* , John | 14,6
Hud | Needs Art | Alex*, John | 12,14,9 | 2days | 2011-03-09 | Yes - Art
Chips | Done | John | 13 | 4days | 2011-03-03 | Yes
Basic Skills(Heal/Blunt) | Done | John | 8,18 | 2days | 2011-03-09 | Yes
Basic Skills(Fire/Slash) | Done | John | 8,18 | 2days | 2011-03-09 | Yes
Lvls 2&3 for skills | Started | John | 8,18 | 3days | 2011-04-04 | yes
Energy Regeneration | Done | Alex, John | 14 | 1day | 2011-03-16 | Yes
Collision | Done | John, Matt | 13 | 3days | 2011-03-16 | Yes
Hub World | Done | Alex, John, Matt* | 7,14 | 2days | 2011-03-16 | Late 1week
Combat | Done | John*, Matt | 14,15 | 4days | 2011-03-16 | Yes
Gear | Started | John | 18 | 4days | 2011-03-24 | Late 3 weeks
Gear - Head | Done | John | 26 |  |  | done
Gear - Chest | Started | John | 26 |  |  | done
Gear - Arms | Started | John | 26 |  |  | done
Gear - Legs | Started | John | 26 |  |  | done
Experience System | Done | Alex, John*, Joe | 14,15,16 | 2days | 2011-03-24 | Late 2 weeks
Personal Stat Progresion | Done | Alex | 14,31 | 3days | 2011-03-24 | Late 2 weeks
Personal Stat Progresion - Display | Done | Alex | 32 |  |  | done
Personal Stat Progresion - Interact | Done | Alex | 12,32 |  |  | done
Chip Leveling | Not Implemented | John | 18, 31 | 1day | 2011-03-24 | Late 3 weeks
Medieval World | Done | Alex, John, Matt* |  | 5days | 2011-04-04 | Late 1week
Medieval World - Design | Done | Alex, Matt | 36 |  |  | done-late
Medieval World - Implement | Done | Alex, John, Matt | 7,13,14,15,23,24 |  |  | late 1month
Dungeon | Done | Alex*, Matt | 36, 47 | 3days | 2011-04-04 | Late 2 weeks
Dungeon - Design | Done | Alex | 39 |  |  | done
Dungeon - Implment | Done | Alex, Matt | 39 |  |  | done
Ai | Started | Alex/ Joe | 15 | 1week | 2011-04-04 | Early 1 week
Ai - PathFinding | Started | Joe
Ai - Wander | Done | Alex | 15 |  |  | done
Ai - Chase | Done | Alex | 15 |  |  | needs pathfinding
Ai - Guard | Done | Alex | 15 |  |  | done
Bosses | Done | Alex, John | 6,15,16,18 | 3days | 2011-04-04 | Yes
Bosses - Ai - Cast check | Done | Alex | 47 |  |  | done
Bosses - Skills | Done | John | 47 |  |  | done
Adding Content | Started | Alex, John, Matt | 36,39 |  |  | In Progress
NPC | Started | Matt/Alex | 10,13 | 4 days | 2011-04-10 | Yes
Character Saves/Loads | Done | Matt | 14, 18,26 | 3days | 2011-04-04 | Late 1 week
Save/Load - Stats | Done | Matt | 14 |  |  | done
Save/Load - Gear | Done | Matt | 18,26 |  |  | done
Inventory | Done | John | 18,26 | 5days | 2011-04-15 | Done
Chips sold for Exp | Not Started | John |  | 1day | 2011-04-15 | Behind
Pickup items | Not Started | John | 55 | 1day | 2011-04-15 | Behind
Seeable Drops | Not Started |  | 57 | 2days | 2011-04-15 | Behind
Potions | Done | Alex | 58 | 2days | 2011-04-15 | Behind- Done
Magic Effects | Done | John | 21 | 3days | 2011-04-28 | Done
Threat | Hold |  |  | 3days | 2011-04-28
Dynamic Monsters Lvls | Done | Alex | 14-16 | 3days | 2011-04-28
World Barriers | Not Started | Alex | 36 | 2days | 2011-05-16
Summons | Not Started |  | 13,18,42 | 3days | 2011-05-16
Magic Combos | Not Started |  | 61 | 2days | 2011-05-16
Flavor Text | Not Started |  | 10, 18,26 | 2days | 2011-05-16
Difficulty Settings | Not Started |  | 63 | 1day | 2011-05-16
Quests | Not Started |  | 51 | 3days | 2011-05-25
Cutscenes | Not Started |  | 9,10,51 | 2days | 2011-05-25
Remaining Worlds | Not Started |  | 5, and all else done | 3weeks | 2011-06-01
Basic Networking | Done | Alex |  | 2week | 2011-03-16 | Early 1 week
Chat System (console) | Done | Alex |  | 3days | 2011-03-21 | yes
Sync Ai | On Hold | Alex |  | 2days | 2011-04-11 | On Hold/Late
Id Auras | Not Started |  |  | 2days
Chat System In Game | Not Started |  |  | 1week
Trade Window | Not Started |  |  | 4days